## Social Media Plan Template
Event Planning Template | Looking for a platform to host your next event? Book a Demo
Task Name | Status | Start Date | Due Date | Assigned To | Flagged | Description
GET STARTED WITH THIS PROJECT TEMPLATE | Not Started |  |  |  | Flagged | This project template is designed to you to effectively plan a small to medium-sized event with a 6 week lead time, covering all the areas required to make sure it's a success.
INITIAL PLANNING - 6+ WEEKS PRIOR TO EVENT | Not Started |  |  |  | Flagged | When planning a smaller event, you still need to leave plenty of time to give notice to your audience and other stakeholders.
Create Event Overview | Not Started | 2021-06-29 | 2021-06-29 |  | Not Flagged | The event overview helps to set the frame for your event and to lay out all of the key points for it. > Define the purpose of the event > Choose the format (e.g. awards night, conference, presentation, etc.) > Select a date for the event > Set a budget > Create the event's title > Plan the times for the event.
Define Event Scope | Not Started |  | 2021-07-01 |  | Not Flagged | > State the target audience > Plan the messaging > Outline the objectives of the event > Prepare the guest list (e.g. speakers, exhibitions, etc.) > Prepare a risk management checklist > Finalize the budget.
Choosing Virtual Event Platform | Not Started | 2021-07-04 | 2021-07-05 |  | Not Flagged | You'll need to make sure you find the right platform to host your event for the date that you've got planned. > Research platform options > Book a Demo to test it > Clarify if the venue is providing staff or if you need to book
Establish Event Publicity Plan | Not Started |  | 2021-07-04 |  | Not Flagged | What needs to be done, who will do it, and when? > Design any assets that can help to support promotion of event
Planning Core Participants | Not Started |  | 2021-07-05 |  | Not Flagged | > Decide if there will be entertainment required, like gamification options > Prepare a list of possible key guests / speakers to contact.
4-5 WEEKS BEFORE EVENT | Not Started |  |  |  | Flagged
Book Guests / Speakers | Not Started |  | 2021-07-07 |  | Not Flagged | > Contact guests / speakers from the short list > Clearly & precisely articulate your goals for the event
Prepare Assets for Event |  | 2021-07-09 | 2021-07-14 |  | Not Flagged | > Organize room customization (if applicable) > Brief the speakers on the event and what to expect.
Begin Promoting the Event | Not Started | 2021-07-14 | 2021-08-04 |  | Not Flagged | > Update your website, social media & ask partners to do the same > Identify channels for contacting and inviting guests (Meetup, LinkedIn, Facebook, Twitter, Email, Phone, etc.) > Send invites to target guests > Create & send a press release.
2-3 WEEKS BEFORE EVENT | Not Started |  |  |  | Flagged
Confirm Attendance & Other Requirements | Not Started |  | 2021-07-23 |  | Not Flagged | > Confirm staff to host event > Prepare run sheet and distribute to all parties.
Confirm Virtual Event Platform | Not Started |  | 2021-07-23 |  | Not Flagged | Confirm that everything is still on track with the platform
DAY BEFORE EVENT | Not Started |  |  |  | Flagged
Finalize Preparation for Event | Not Started | 2021-07-31 | 2021-08-04 |  | Not Flagged
Update Run Sheet (if required) | Not Started | 2021-08-03 | 2021-08-04 |  | Not Flagged
Undertake Soundcheck & Visuals | Not Started | 2021-08-04 | 2021-08-04 |  | Not Flagged
DAY OF EVENT | Not Started |  |  |  | Flagged
Update Run Sheet (if required) | Not Started |  | 2021-08-05 |  | Not Flagged | Communicate any last minute changes.
Conduct Event Set Up |  |  | 2021-08-05 |  | Not Flagged | > Set up virtual signs and instructions > Run through the event with key stakeholders (MC, speakers, entertainment, etc.) > Have virtual gifts to hand (if relevant) > Ensure audio visual set up is running per schedule
POST-EVENT WEEK 1 | Not Started |  |  |  | Flagged | When the event is over and everyone is gone home, there's still some post-event work which needs to be completed. These allow you to round up the event and to gather valuable feedback to help you determine the level of success.
Prepare Post Event Follow Up | Not Started |  | 2021-08-12 |  | Not Flagged | > Collect guest / speaker / volunteer feedback > Prepare thank you emails for all parties involved (e.g. speakers, patrons, entertainment, committee etc.) > Review event's performance vs. expectations > Pay any outstanding fees to suppliers, speakers, staff, etc.
Formulas:
Due Date = [Start Date]
Due Date = [Start Date, row above]+2